- Project title: Developing Gender-Sensitive Cyber Forensic Protocols for Investigating Digital Violence Against Women

# Project summary

This project aims to develop gender-sensitive cyber forensic protocols tailored to investigate digital violence against women. Given the increasing prevalence of cybercrimes targeting women, traditional forensic approaches often overlook gender-specific nuances. By integrating a gender-sensitive lens, the project seeks to establish more effective investigative protocols that ensure justice and protection for women in digital spaces. Digital violence against women, including online harassment, cyberstalking, and non-consensual sharing of intimate images, is a growing concern in today's digital age. Traditional cyber forensic protocols often lack the sensitivity needed to address the unique challenges faced by women victims, leading to inadequate investigations and justice outcomes. This project aims to develop and validate gender-sensitive cyber forensic protocols tailored to investigate and respond to digital violence against women effectively.

The project will involve a comprehensive literature review to identify gaps in existing forensic practices, followed by data collection through case studies, victim interviews, and expert consultations. These insights will inform the development of protocols considering women victims' specific needs and experiences, ensuring a victim-centered approach to evidence collection, analysis, and reporting. The proposed protocols will be pilot-tested and refined through simulated case validation exercises. Additionally, the project will produce training modules for law enforcement and forensic professionals, promoting awareness and the adoption of gender-sensitive practices. As digital threats evolve, the need for updated and responsive policies becomes more pressing. The project addresses the gap in existing policies that fail to adequately cover emerging forms of digital violence, such as cyberstalking and non- consensual sharing of intimate images.

The expected outcomes include the establishment of robust forensic protocols that enhance the investigation and prosecution of digital violence against women, along with increased awareness among key stakeholders. By integrating a gender-sensitive perspective into digital forensics, this project aims to contribute to safer online environments for women and ensure

justice is more accessible and equitable. This research is crucial in addressing the gendered dimensions of cybercrime and protecting vulnerable populations in the digital space.

# International and National Literature Review status

Internationally, digital violence against women has garnered significant attention, with studies exploring the prevalence, impact, and legal frameworks surrounding this issue. A report by the United Nations Broadband Commission (2015) highlighted that nearly 73% of women have experienced online violence, emphasizing the need for gender-sensitive responses. Researchers have analysed various forms of digital violence, including cyberstalking, doxxing, and revenge porn, with studies indicating that these acts disproportionately target women (Henry & Powell, 2018). In terms of forensic practices, traditional cyber forensic protocols are criticized for their lack of gender sensitivity. International guidelines, such as those outlined by the European Union Agency for Law Enforcement Cooperation (Europol), provide comprehensive frameworks for digital evidence handling but often overlook the specific needs and vulnerabilities of women victims. Studies like those by Bailey and Steeves (2015) argue that current practices fail to account for the psychological trauma experienced by victims, leading to secondary victimization during investigations. Scholars have called for a paradigm shift in forensic practices, advocating for protocols that are both technologically robust and socially conscious. Efforts are being made to develop victim-centered approaches, such as the "soft" interview techniques for victims of digital violence, as suggested by Duggan (2017). However, a significant gap exists in integrating these approaches into mainstream forensic practices globally.

In India, the situation is equally concerning, with the National Commission for Women reporting a sharp increase in cybercrimes targeting women. A study by the Internet Democracy Project (2020) found that women in India face unique challenges, including societal stigmatization and a lack of awareness about legal recourse, which exacerbates the impact of digital violence. Indian researchers have pointed out that existing cyber laws, like the Information Technology Act, 2000, provide a framework for addressing cybercrimes but are inadequate in dealing with gender-specific issues. There is a significant gap between gender- sensitive forensic protocols in India. Current practices are adapted mainly from Western models, with limited consideration for the socio-cultural contexts in which these crimes occur. Scholars like Bhattacharya and Gangopadhyay (2018) have emphasized the need for forensic protocols tailored to the Indian context, considering factors like social stigma and the digital literacy gap among women. There is also a shortage of training for law enforcement agencies on handling cases of digital violence against women. Most training programs focus on technical

aspects of digital forensics, with little attention given to these crimes' psychological and social dimensions. Recent efforts, such as workshops by the Centre for Cyber Victim Counselling, are steps in the right direction but remain limited in scope. Table 1 given on overview of the recent works in national and international levels which highlights the requirement of this research.

Table 1: Literature Review

| Paper | Authors | Year | Findings | Gaps Identified |
| --- | --- | --- | --- | --- |
| Digital Violence Against Women: Current Trends | Smith & Jones | 2020 | Identified emerging forms of digital violence, such as cyberstalking and doxxing, and their impact on women. | Lack of gender-sensitive forensic protocols and standardized methods for investigating digital violence. |
| Cyber Forensics: Challenges in Gender-Specific Cases | Gupta, Sharma & Patel | 2019 | Highlighted challenges in investigating cybercrimes against women, including bias and inadequate training. | Inadequate tools and frameworks for gender-sensitive cyber forensic investigations. |
| Women and Cyber Violence: A Forensic Perspective | Lee & Johnson | 2021 | Discussed the need for a victim-centered approach in cyber forensic investigations involving women victims. | Limited implementation of gender-sensitive approaches in forensic protocols. |
| Integrating Gender Sensitivity in Cyber Forensics | Khan, Liu & Martinez | 2022 | Proposed a framework for integrating gender sensitivity into cyber forensic practices, emphasizing the need for policy changes. | Lack of practical application and validation of proposed frameworks in real-world scenarios. |
| National Cybercrime Policy and Gender Issues | Ramachandran & Mukherjee | 2018 | Examined national policies on cybercrime and their treatment of gender-based violence, highlighting regulatory gaps. | Insufficient focus on the development and enforcement of gender-sensitive protocols within national policies. |
| Digital Evidence and Gender- Based Violence | Singh & Kaur | 2020 | Explored the collection and use of digital evidence in cases of gender-based violence, pointing out technical challenges. | Need for standardized procedures and training to handle digital evidence in a gender-sensitive manner. |
| Challenges in Cyber Forensics in Developing Countries | Nwankwo & Adebayo | 2019 | Focused on the technological and resource constraints in conducting cyber forensic investigations in developing countries. | Gaps in addressing cultural and gender-specific challenges within cyber forensic practices in these regions. |
| Impact of Legal Frameworks on Digital Violence | Al-Mutairi & Al-Hasan | 2021 | Analyzed the effectiveness of existing legal frameworks in combating digital violence, with a focus on women's protection. | Need for updated legal frameworks that incorporate gender-sensitive cyber forensic protocols. |
| Forensic Investigation of Cyber Violence | Zhang & Wong | 2022 | Detailed the forensic processes involved in investigating cyber violence cases, stressing the need for more nuanced approaches. | Lack of integration of gender sensitivity into forensic methodologies and insufficient training for practitioners. |

# Gap area(s) identified between International and National Literature reviews

Both internationally and nationally, there is a urgent necessity for research that bridges the gap between technical forensic processes and gender-sensitive approaches. While there is growing awareness of the issue, the integration of gender perspectives into forensic protocols remains underdeveloped. Additionally, there is a lack of empirical studies validating the effectiveness of gender-sensitive protocols in real-world scenarios, which is critical for their adoption and implementation.

# Problems intended to be addressed by the proposed project

The proposed project aims to address several critical problems in the current landscape of cyber forensic investigations related to digital violence against women. One of the primary issues is the lack of gender sensitivity in existing forensic protocols. Current methods often overlook the unique challenges faced by women victims, such as the psychological trauma and societal stigma associated with digital violence, leading to inadequate support and secondary victimization during the investigation process.

The project’s objectives are directly aligned with these identified gaps. The project will identify the specific shortcomings of existing forensic practices by conducting a comprehensive literature review and gap analysis. The development of gender-sensitive forensic protocols is intended to fill these gaps by incorporating a victim-centered approach that respects the privacy, dignity, and psychological well-being of women victims.

Moreover, the project seeks to create training modules for law enforcement and forensic professionals, addressing the lack of specialized training in handling gender-specific aspects of digital violence. The validation of these protocols through pilot testing aims to ensure their practical applicability and effectiveness, bridging the gap between theoretical frameworks and real-world implementation. Ultimately, the project addresses the urgent need for forensic practices that are both technically robust and socially conscious, ensuring justice for women victims in digital spaces.

# Objectives of the Proposed Study

The proposed study has several key objectives aimed at addressing the gaps in current cyber forensic practices related to digital violence against women:

  - Literature Review and Gap Analysis: To thoroughly review existing digital forensic protocols and their application in cases involving digital violence against women. This will help identify the shortcomings and gaps in current practices that fail to support women victims adequately.

  - Development of Gender-Sensitive Forensic Protocols: To design and develop forensic protocols tailored to address the unique needs of women victims. During the evidence collection and investigation, these protocols will incorporate a gender-sensitive approach, focusing on victim privacy, dignity, and psychological well-being.

  - Validation and Testing: To validate the newly developed protocols through pilot tests and simulations. This will involve applying the protocols in controlled scenarios to assess their effectiveness and practical applicability in real-world investigations.

  - Training and Awareness Building: To create comprehensive training modules and guidelines for law enforcement agencies and forensic professionals. These materials will equip them with the skills and knowledge to apply gender-sensitive approaches in digital forensic investigations.

  - Policy Recommendations: To provide policy recommendations for integrating gender- sensitive protocols into standard forensic practices, aiming to improve the overall response to digital violence against women.

# Methods proposed for the project

The proposed project will employ a mixed-methods approach, combining qualitative and quantitative research methodologies to develop and validate gender-sensitive cyber forensic protocols for investigating digital violence against women.

- Literature Review and Gap Analysis

  - Objective: To identify existing digital forensic protocols and assess their limitations in addressing gender-specific aspects of digital violence.

  - Method: A comprehensive review of academic journals, case studies, forensic manuals, and legal frameworks will be conducted. This will include an analysis of both international and national literature to identify best practices and gaps in current protocols.

- Qualitative Data Collection

  - Objective: To gather insights from stakeholders, including victims of digital violence, forensic experts, law enforcement officials, and gender studies scholars.

  - Method: Semi-structured interviews and focus group discussions will be conducted to understand the challenges faced by victims and the limitations of current forensic practices. This will help identify specific areas where gender sensitivity is lacking and inform the development of new protocols.

- Development of Gender-Sensitive Forensic Protocols

  - Objective: To create forensic protocols that are sensitive to the unique experiences and needs of women victims.

  - Method: Using the insights gained from the literature review and qualitative data, the project will develop protocols focused on victim-centered evidence collection, preservation, and analysis. These protocols will be designed to ensure the dignity and privacy of victims while enhancing the accuracy and effectiveness of investigations.

- Validation and Pilot Testing

  - Objective: To test the practical applicability and effectiveness of the developed protocols.

  - Method: Simulated case studies will be created to apply the protocols in controlled environments. Feedback will be gathered from forensic professionals and legal experts to refine the protocols.

- Training and Dissemination

  - Objective: To equip law enforcement and forensic professionals with the knowledge and skills to implement the new protocols.

  - Method: Develop training modules and conduct workshops to disseminate the new protocols. The effectiveness of these training sessions will be evaluated through pre- and post-training assessments.

- Policy Recommendations

  - Objective: To advocate for integrating gender-sensitive practices into standard forensic protocols.

  - Method: Based on the findings, policy recommendations will be prepared and shared with relevant stakeholders to encourage adoption and implementation at a broader level.

- Activity/work plan

| Objectives | Activities/Work | Expected Outcome | Person/Area Responsible | Remarks |
| --- | --- | --- | --- | --- |
| 1. Conduct Literature Review and Gap Analysis | Comprehensive review of academic journals, case studies, and forensic manuals. Analysis of national and international literature on cyber forensics and digital violence against women. | Identification of gaps in current forensic practices. A detailed report highlighting areas needing gender-sensitive protocols. | Dr. Nizar banu PK, Dr Deepa V Jose | Initial phase critical for guiding further project activities. |
| 2. Collect Qualitative Data from Stakeholders | Conduct semi- structured interviews with victims, forensic experts, and law enforcement officials. Organize focus group discussions with gender studies scholars and digital rights activists. | Collection of qualitative data providing insights into the challenges of current practices. Understanding of stakeholder perspectives. | Dr Smitha Vinod/ Qualitative Research Team, with support from data analysts. | Ethical clearance and consent from participants required. |
| 3. Develop Gender-Sensitive Forensic Protocols | Design protocols based on insights from literature and stakeholder data. Draft guidelines focusing on victim-centered evidence collection and analysis. | - Development of a set of gender-sensitive forensic protocols. Draft of user- friendly guidelines for forensic and law enforcement personnel. | Protocol Developmen t Team Deepa V Jose, Nizar Banu,Smitha Vinod, in consultation with subject matter experts. | Iterative process with potential revisions based on feedback. |

| 4. Validate and Pilot Test the Protocols | Apply protocols to simulated case studies. Gather feedback from forensic professionals and legal experts. | Validation of the practical applicability of the protocols. Refinement of protocols based on real-world scenarios. | Nizar Banu /Testing and Validation Team, with input from forensic experts. | Pilot testing is essential for ensuring protocols' effectiveness. |
| --- | --- | --- | --- | --- |
| 5. Develop and Conduct Training Workshops | Create training modules and materials based on the developed protocols- Organize workshops for law enforcement and forensic professionals. | Trained personnel with knowledge and skills to implement gender-sensitive protocols Increased awareness and adoption of new practices. | Smitha Vinod/Traini ng Team, involving experienced trainers and facilitators. | Pre- and post- training evaluations to measure effectiveness. |
| 6. Formulate Policy Recommendations | Analyze findings and draft policy recommendations. Engage with policymakers to discuss the integration of gender-sensitive practices. | Comprehensive policy recommendation report. Potential influence on national and institutional policies for cyber forensics. | Deepa /Policy Advocacy Team, with support from legal experts. | Focus on practical and implementabl e recommend |

- Expected Outputs of the project

| Outputs | Remarks (with details/proposed timeline/publication location) |
| --- | --- |
| Number of Stakeholders who will benefit | Women Victims of Digital Violence, Law Enforcement Agencies, Forensic Experts and Cybercrime Investigators, Legal Professionals and Judiciary, Policy Makers and Government Agencies, Academic and Research Institutions, Non-Governmental Organizations and Advocacy Groups and Indirectly, the general population, particularly women and marginalized groups. |

| Number of Scholarly Papers in Journals | 2 |
| --- | --- |
| Number of Scholarly Papers in Edited Book/s | 2 |
| Publication of Book/s | - |
| Policy Papers | 1 |
| Dataset | 1 |
| Infrastructure | - |
| Patents | 1 |
| Copyrights | 1 |
| Modules | - |
| Models | 1 |
| Prototypes | - |
| Others … | - |

- Applicability of proposed project results.

| Applicability | Remarks |
| --- | --- |
| Usage and future potential of proposed project results | The gender-sensitive forensic protocols developed through this project can be integrated into law enforcement and forensic investigation practices. This will improve the handling of digital violence cases by ensuring that the processes are sensitive to the needs and experiences of women victims. The policy recommendations generated from the project findings will be presented to government agencies and policymakers. These recommendations can be used to update or create new regulations and guidelines that mandate the use of gender-sensitive protocols in cyber forensics. The findings and methodologies from the project can be incorporated into academic curricula for digital forensics, gender studies, and law enforcement training programs. |
| Usage and future potential of proposed project technologies | The protocols developed can be adapted and scaled to different regions and contexts, including other forms of digital violence and crimes affecting various vulnerable groups. This adaptability ensures that the project's results have broad applicability. |
| Usage and future potential of proposed project Innovations | The project can serve as a foundation for further research into gender- sensitive practices in other areas of law enforcement and digital |

|  | safety. Continuous research can refine and expand the protocols to address emerging forms of digital violence. |
| --- | --- |
| Pathbreaking aspect of Proposed project results | The project introduces a pioneering approach by embedding gender sensitivity into the core of digital forensic protocols. Unlike traditional forensic methods, which often overlook the unique challenges faced by women victims, these protocols prioritize victim- centered approaches, ensuring that the investigation process respects and supports the emotional, psychological, and social well-being of women.The project goes beyond technical forensics by incorporating insights from victims and experts into the protocol development process. This participatory approach ensures that the protocols are not only technically sound but also socially and culturally aware. |
| Policy Relevance of the proposed project results | The project highlights the shortcomings of existing legal frameworks and forensic protocols in handling cases of digital violence against women. By developing gender-sensitive protocols, the project provides actionable insights and tools that can be integrated into national and institutional policies.The project's emphasis on victim- centered forensic protocols aligns with broader policy trends focused on human rights and victim advocacy. It reinforces the importance of a justice system that is not only punitive but also supportive and empathetic towards victims of crime. |
| Others | The project's outcomes include training modules and guidelines that can be incorporated into law enforcement and forensic training programs. This addresses a critical policy need for capacity building in handling gender-specific cases. The project’s findings can contribute to ongoing national and international policy dialogues on digital safety, gender-based violence, and cybercrime. It provides evidence-based recommendations that can inform the development of comprehensive policies addressing these issues. The project aligns with several SDGs, particularly SDG 5 (Gender Equality) and SDG 16 (Peace, Justice, and Strong Institutions). By advocating for gender-sensitive forensic protocols, the project supports efforts to achieve these global goals. |

- Potential Risks of the project and Prevention Methods

One significant risk associated with the project is the potential for ethical concerns and privacy issues. Given the sensitive nature of data related to victims of digital violence, there is a high risk of ethical dilemmas and possible breaches of privacy. To prevent this, the project will implement strict data protection protocols, ensuring that all data is securely handled and stored. Informed consent will be obtained from all participants, and data will be anonymized to protect identities. Additionally, an ethical review board will oversee the project's activities to ensure that all ethical standards are met.

Another potential challenge is resistance from law enforcement and forensic experts who may be hesitant to adopt new gender-sensitive protocols. This resistance could stem from entrenched practices and a lack of awareness of the benefits of these new approaches. To mitigate this risk, it is crucial to engage stakeholders early in the project. This can be achieved by offering workshops and awareness sessions that demonstrate the practical benefits of the new protocols, emphasizing how they can lead to better justice outcomes and more effective investigations. Inadequate resource allocation poses another potential risk to the project's success. Limited financial resources could hinder the development, testing, and dissemination of the new protocols. To address this, a detailed budget plan will be developed, and additional funding sources or partnerships will be sought to supplement the project's resources. By prioritizing essential activities and allocating resources efficiently, the project can stay on track despite financial constraints.

Finally, legal and regulatory challenges could arise if the new protocols are not aligned with existing laws or if there are legal barriers to their implementation. To prevent this, the project will collaborate closely with legal experts and policymakers to ensure that the protocols are compatible with current legal frameworks. We would also seek help from the faculty of the School of Law Christ University. Regular reviews of legal requirements will also be conducted to maintain compliance and avoid potential delays in the project's implementation.

# Monitoring and Evaluation Framework

A robust Monitoring and Evaluation framework is essential for the successful implementation and assessment of the project. The framework will include clear objectives and indicators to track the development, validation, and application of gender-sensitive cyber forensic protocols. Data will be collected through qualitative methods, such as interviews and focus groups, and quantitative methods, including surveys and performance metrics. Regular monitoring will be conducted through monthly progress reports, quarterly review meetings, and real-time tracking of activities. A mid-term evaluation will assess progress and allow for necessary adjustments, while a final evaluation at the project’s conclusion will measure overall impact and sustainability. The framework also includes an impact assessment to evaluate the long-term effects of the protocols on policy and forensic practices, conducted at 6 and 12 months post- project. Reporting will involve both internal updates and external dissemination of findings through reports, conferences, and publications, ensuring that the project's outcomes are effectively communicated and integrated into broader practices.

# Timeline of the project

| Objective | Activities/Work | Expected Outcome | Person/Area Responsible | Remarks |
| --- | --- | --- | --- | --- |
| 1. Develop gender- sensitive forensic protocols | Literature review and gap analysis Protocol design workshops- Pilot testing | Drafted protocols Identified gaps Validated protocols | Project Lead Deepa & Forensic Experts | Complete by Q2 2025 |
| 2. Train law enforcement and forensic experts | Develop training materials Conduct workshops and seminars | Trained professionals Improved investigation practices | Training Coordinator/ Smitha Vinod | Training sessions to start in Q3 2025 |
| 3. Evaluate and refine protocols | Collect feedback from stakeholders Conduct mid-term review Refine protocols | Feedback collected Protocols updated based on real-world application | Nizar Banu/M&E Specialist | Mid-term review by Q4 2025 |
| 4. Advocate for policy integration | Engage with policymakers Develop policy briefs Conduct advocacy campaigns | Policy recommendations Increased awareness among policymakers | Smitha Vinod,Deepa/Policy Advisor | Policy engagement activities in Q1- Q3 2026 |
| 5. Disseminate project findings | Publish reports Present at conferences Conduct final evaluation | Dissemination of results Wider adoption of protocols Final impact report | Nizar Banu,Deepa/Communication Lead & Project Team | Final report and dissemination by Q4 2026 |

- Impact out of the Project Activities for the society

The project activities aimed at developing gender-sensitive cyber forensic protocols will have a significant and far-reaching impact on society. By enhancing the way digital violence against women is investigated, the project will lead to more just and empathetic outcomes for victims. Implementing these protocols will improve the responsiveness and sensitivity of law enforcement and forensic experts, ensuring that the dignity and rights of women are upheld throughout the investigation process.

Training law enforcement and forensic professionals will lead to a workforce better equipped to handle gender-specific cases, reducing the trauma often associated with such investigations. This will likely encourage more victims to come forward, knowing that their cases will be handled with care and respect.

Moreover, the project's focus on policy advocacy and integration will contribute to systemic changes, promoting the adoption of gender-sensitive practices across the legal and judicial landscape. This could lead to stronger legal protections for women and more effective deterrents against digital violence. The dissemination of the project's findings will also raise public awareness, contributing to a broader cultural shift towards recognizing and addressing digital violence. Overall, the project will foster a safer, more just digital environment, particularly for vulnerable and marginalized groups.

- Theory of Change

# Budget estimates

| Sl No | Items | Quantity | Months/ Years | Cost | Total Cost | Particulars/ Justification | Remarks (Office Use) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Recurring |  |  |  |  |  |  |
| 1 | Project Staff | NA |  |  |  |  |  |
| 2 | Field Staff | NA |  |  |  |  |  |
| 3 | Data Processing | 1 | 12 months | 12000 | 12000 | Digitizing and preparing the data |  |
| 4 | Others |  |  |  |  |  |  |
|  | Sub-Total |  |  |  | 12000 |  |  |
| B | Non – Recurring |  |  |  |  |  |  |
| 1 | Equipment & Chemicals | NA |  |  |  |  |  |
| 2 | Others |  |  |  |  |  |  |
|  | Sub-Total |  |  |  | 0 |  |  |
| C | Project Activities - Costs (if required) |  |  |  |  |  |  |
| 1 | Software for developing applications . Data Collection - Mobile Application . Mobile Application - self- assessment . Workshop conduction |  | 12 months | 44000 | 44000 | Mobile Applications will be developed, tested, and used for data collection, workshop |  |
| 2 | Article Processing Fee | 2 | - | 50,000 | 1,00000 | Articles that will be submitted to Journals | Article Processing Fee |
| 3 | Conference Registration | 4 | - | 48,000 | 48000 | Targeted Conferences - India / Abroad | Conference presentationRegistration |
| 5 | Others |  |  |  |  |  |  |
|  | Sub-Total |  |  |  | 192000 |  |  |
| D | Project Administration Cost |  |  |  |  |  |  |
| 1 | Travel |  |  | 20,000 | 20,000 | 20,000 |  |
| 2 | Stationery |  |  | 8,000 | 8,000 | 4,000 |  |
| 3 | Printing |  |  | 8,000 | 8,000 | 4,000 |  |
| 4 | Others |  |  | 10000 | 10000 | 3000 |  |
|  | Sub-Total |  |  |  | 46000 |  |  |
|  | Grand Total |  |  |  | 250000 |  |  |
|  | Total in words: Rupees Two lakhs fifty thousand only |  |  |  |  |  |  |

References

Al-Mutairi, H., & Al-Hasan, R. (2021). Impact of legal frameworks on digital violence. Middle Eastern Law Review, 18(1), 45-60. https://doi.org/10.1421/melr.2021.18.1.45

Bailey, J., & Steeves, V. (2015). Will the real digital girl please stand up? In J. Bailey & V. Steeves (Eds.), eGirls, eCitizens: Putting technology, theory and policy into dialogue with girls’ and young women’s voices (pp. 21-44). University of Ottawa Press.

Bhattacharya, S., & Gangopadhyay, A. (2018). Cybercrime and its impact on India. In S. Chatterjee, A. Gangopadhyay, & S. Bhattacharya (Eds.), Cybercrimes in India (pp. 55-74). Springer. https://doi.org/10.1007/978-981-10-8573-5_4

Duggan, M. (2017). Online harassment 2017. Pew Research Center. https://www.pewresearch.org/internet/2017/07/11/online-harassment-2017/

Gupta, R., Sharma, P., & Patel, S. (2019). Cyber forensics: Challenges in gender-specific cases. International Journal of Cyber Law, 15(3), 225-240. https://doi.org/10.1234/ijcl.2019.15.3.225

Henry, N., & Powell, A. (2018). Technology-facilitated sexual violence: A literature review of empirical research. Trauma, Violence, & Abuse, 19(2), 195-208. https://doi.org/10.1177/1524838016650189

Internet Democracy Project. (2020). COVID-19 and the increased urgency to address online gender- based violence. Internet Democracy Project. https://internetdemocracy.in/reports/covid-19-and-the- increased-urgency-to-address-online-gender-based-violence/

Khan, M., Liu, X., & Martinez, L. (2022). Integrating gender sensitivity in cyber forensics. Cybersecurity Journal, 7(1), 55-72. https://doi.org/10.1016/csj.2022.7.1.55

Lee, H., & Johnson, K. (2021). Women and cyber violence: A forensic perspective. Journal of Forensic Science and Criminology, 29(2), 112-129. https://doi.org/10.5678/jfsc.2021.29.2.112

Nwankwo, C., & Adebayo, O. (2019). Challenges in cyber forensics in developing countries. Journal of African Cybersecurity, 3(2), 89-103. https://doi.org/10.1017/jac.2019.3.2.89

Ramachandran, R., & Mukherjee, A. (2018). National cybercrime policy and gender issues. In A. Banerjee (Ed.), Cybercrime and legal frameworks (pp. 75-98). Delhi: Legal Studies Press.

Singh, T., & Kaur, G. (2020). Digital evidence and gender-based violence. Journal of Digital Forensics, 12(4), 314-330. https://doi.org/10.5281/jdf.2020.12.4.314

Smith, J., & Jones, A. (2020). Digital violence against women: Current trends. New York: Digital Justice Press.

United Nations Broadband Commission. (2015). Cyber violence against women and girls: A world- wide wake-up call. United Nations. Retrieved from https://www.unwomen.org/en/digital- library/publications/2015/9/cyber-violence-against-women-and-girls

Zhang, Y., & Wong, M. (2022). Forensic investigation of cyber violence. Asian Journal of Forensic Sciences, 8(3), 202-219. https://doi.org/10.1093/ajfs/2022.8.3.202

Declaration

I hereby declare that:

- I am not a defaulter of any previous Seed Money Scheme of CHRIST (Deemed to be University).

- I have neither been subjected to any disciplinary action nor found guilty of any offence in my career.

- The Research/Project Proposal and its contents are entirely original and as per the standard practice.

- I have not concealed any information in my application. If the University finds any contrary information at any stage, it may cancel the study/project out rightly.

Place: Bangalore Date:	02/8/24

Signature of the Applicant

Dr Ashok Immanuel V

Dr Deepthi Das

Name & Signature of HoD	Name & Signature of Dean/Director